## Slide 1
HARROWGATE FIELD SERVICES
Willowmere Phase 3
Project kickoff · contract WM-2026-114
46 hectares of restored grazing marsh, 1.9 km of reprofiled ditch, and a delivery window that closes on 31 March 2027.
6 August 2026 · Prepared for the Willowmere steering group

## Slide 2
Where Phase 2 leaves us
• Reed establishment reached 74%, against a 60% target
• Standing water held through a 19-day dry spell
• Breeding waders returned to compartment 2
• Silt from the northern culvert is 2.4× the modelled rate
• Bank slumping at chainage 0+840 needs regrading
• No invasive species found inside the boundary
74%
reed cover
46.3 ha
surveyed
11
survey days
2.4×
silt load

## Slide 3
Phase 3 milestones
WHEN
MILESTONE
OWNER
Sep 2026
Bank regrade and reseed complete
Site team
Oct 2026
Settlement pocket enlarged, silt trap in
Contractor
Dec 2026
Winter water-level regime signed off
Hydrology
Feb 2027
Eastern dipwell network extended
Survey
Mar 2027
Phase 3 handover and final report
All